## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 01. User Management | 1.05 | View Order History | Search for Proper UI Design | N | 2025-04-09 | 2025-04-15 | 100% | Saily
2 | 01. User Management | 1.05 | View Order History | Implement API for order history retrieval | Y | 2025-04-09 | 2025-04-14 | 100% | Kuldeep
3 | 01. User Management | 1.05 | View Order History | Implement role-based access control | N | 2025-04-11 | 2025-04-15 | 100% | Kuldeep
4 | 01. User Management | 1.05 | View Order History | Implement sorting and filtering functionality | Y | 2025-04-11 | 2025-04-16 | 100% | Saily
5 | 01. User Management | 1.05 | View Order History | Add pagination for large order lists | N | 2025-04-12 | 2025-04-17 | 100% | Saily
6 | 01. User Management | 1.05 | View Order History | Perform exploratory testing on order history | N | 2025-04-12 | 2025-04-18 | 100% | Tarun
7 | 01. User Management | 1.05 | View Order History | Validate role-based access controls | N | 2025-04-13 | 2025-04-19 | 100% | Dezil
8 | 01. User Management | 1.05 | View Order History | Test performance with large datasets | N | 2025-04-13 | 2025-04-20 | 95% | Fouzan
9 | 02. Restaurant Management | 2.05 | Update Menu Offerings | Design backend API for menu item updates | Y | 2025-04-13 | 2025-04-15 | 95% | Kuldeep
10 | 02. Restaurant Management | 2.05 | Update Menu Offerings | Create UI for restaurant owners to edit menu items | N | 2025-04-09 | 2025-04-15 | 95% | Saily
11 | 02. Restaurant Management | 2.05 | Update Menu Offerings | Implement real-time menu sync across platform | Y | 2025-04-10 | 2025-04-11 | 95% | Fouzan
12 | 02. Restaurant Management | 2.05 | Update Menu Offerings | Add validation for pricing and availability changes | N | 2025-04-10 | 2025-04-11 | 95% | Saily
13 | 02. Restaurant Management | 2.05 | Update Menu Offerings | Test menu update functionality with various item types | N | 2025-04-10 | 2025-04-11 | 95% | Tarun
14 | 03. Order and Payment Processing | 3.01 | Place Food Order | Search for Proper UI Design | N | 2025-04-10 | 2025-04-11 | 95% | Saily
15 | 03. Order and Payment Processing | 3.01 | Place Food Order | Implement API for order submission | Y | 2025-04-10 | 2025-04-11 | 95% | Kuldeep
16 | 03. Order and Payment Processing | 3.01 | Place Food Order | Implement real-time menu availability checks | Y | 2025-04-11 | 2025-04-12 | 95% | Fouzan
17 | 03. Order and Payment Processing | 3.01 | Place Food Order | Design and implement order cart UI | N | 2025-04-11 | 2025-04-12 | 95% | Saily
18 | 03. Order and Payment Processing | 3.01 | Place Food Order | Implement validation for order items | Y | 2025-04-11 | 2025-04-12 | 95% | Saily
19 | 03. Order and Payment Processing | 3.01 | Place Food Order | Test order submission with various items | N | 2025-04-11 | 2025-04-12 | 95% | Tarun
20 | 03. Order and Payment Processing | 3.01 | Place Food Order | Verify real-time availability updates | N | 2025-04-11 | 2025-04-12 | 95% | Tarun
21 | 03. Order and Payment Processing | 3.01 | Place Food Order | Performance test order submission flow | N | 2025-04-11 | 2025-04-12 | 95% | Dezil
22 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Search for Proper UI Design | N | 2025-04-11 | 2025-04-12 | 90% | Saily
23 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Implement API for ad campaign creation | Y | 2025-04-11 | 2025-04-12 | 90% | Fouzan
24 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Design ad campaign creation form | N | 2025-04-11 | 2025-04-12 | 90% | Saily
25 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Implement budget tracking and limits | Y | 2025-04-09 | 2025-04-15 | 90% | Kuldeep
26 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Add role-based access controls | N | 2025-04-09 | 2025-04-15 | 90% | Fouzan
27 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Test ad campaign creation workflow | N | 2025-04-09 | 2025-04-15 | 90% | Tarun
28 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Verify budget enforcement | N | 2025-04-09 | 2025-04-15 | 90% | Tarun
29 | 04. Advertisement Management | 4.01 | Create Ad Campaigns | Test access control restrictions | N | 2025-04-09 | 2025-04-15 | 90% | Dezil
30 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Design backend for sponsored listing priority system | Y | 2025-04-09 | 2025-04-15 | 90% | Fouzan
31 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Create UI for managing sponsored listings | N | 2025-04-10 | 2025-04-15 | 90% | Saily
32 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Implement budget tracking for sponsored listings | Y | 2025-04-11 | 2025-04-15 | 90% | Kuldeep
33 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Add validation for sponsored listing durations | N | 2025-04-12 | 2025-04-15 | 90% | Saily
34 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Test sponsored listing visibility in search results | N | 2025-04-13 | 2025-04-15 | 90% | Tarun
35 | 07. Customer Support | 7.01 | Track Order Status | Implement API + WebSocket for real-time status updates | Y | 2025-04-09 | 2025-04-20 | 100% | Fouzan
36 | 07. Customer Support | 7.01 | Track Order Status | Design status tracking UI with notifications | N | 2025-04-09 | 2025-04-20 | 100% | Saily
37 | 07. Customer Support | 7.01 | Track Order Status | Test real-time updates under poor network conditions | N | 2025-04-09 | 2025-04-20 | 100% | Dezil
38 | 07. Customer Support | 7.03 | Submit Feedback | Design feedback API + form UI | Y | 2025-04-10 | 2025-04-20 | 100% | Kuldeep
39 | 07. Customer Support | 7.03 | Submit Feedback | Implement content validation and categorization | N | 2025-04-10 | 2025-04-20 | 100% | Saily
40 | 07. Customer Support | 7.05 | Manage FAQs | Build FAQ management API + admin UI | Y | 2025-04-10 | 2025-04-20 | 100% | Fouzan
41 | 07. Customer Support | 7.05 | Manage FAQs | Add search functionality and role-based access | N | 2025-04-11 | 2025-04-20 | 100% | Kuldeep

## S3
Task | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 01. User Management | 1.01 | Register User Account | Create account registration with email/phone verification, captcha, and optional referral code support for tracking signups. | Y | 2025-05-03 | 2025-05-04 | 100% | Dezil
2 | 01. User Management | 1.02 | Log In User | Implement secure user authentication using username, password, and multi-factor authentication (MFA), including session timeout logic. | Y | 2025-04-18 | 2025-04-20 | 100% | Kuldeep
3 | 01. User Management | 1.03 | Manage User Profile | Create comprehensive profile management tools that allow users to update personal information, change profile pictures, and manage preferences. | N | 2025-04-20 | 2025-04-21 | 100% | Saily
4 | 01. User Management | 1.04 | Control Role-Based Access | Design and implement a role-based access control (RBAC) system to assign permissions based on user roles (admin, customer, restaurant owner). | Y | 2025-04-21 | 2025-04-23 | 100% | Fouzan
5 | 02. Restaurant Management | 2.04 | Manage Restaurant Profile | Build admin interface for restaurants to manage address, contact info, hours, and branding with real-time sync. | Y | 2025-05-03 | 2025-05-04 | 100% | Tarun
6 | 02. Restaurant Management | 2.05 | Update Menu Offerings | Develop a user-friendly interface with drag-and-drop support that allows restaurants to update and reorder menu items with real-time previews. | N | 2025-04-23 | 2025-04-24 | 100% | Saily
7 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Provide restaurant staff with a reservation management view, allowing them to view, modify, and confirm or cancel diner reservations. | Y | 2025-05-06 | 2025-05-07 | 100% | Tarun
8 | 03. Order and Payment Processing | 3.02 | Process Secure Payment | Integrate a PCI-compliant third-party payment gateway with tokenization and encryption support for safe online transactions. | Y | 2025-04-24 | 2025-04-25 | 100% | Dezil
9 | 03. Order and Payment Processing | 3.03 | Track Commission Revenue | Implement logic for tracking platform commission on each transaction, including integration with vendor dashboards. | N | 2025-04-30 | 2025-05-01 | 100% | Saily
10 | 04. Advertisement Management. | 4.01 | Create Ad Campaigns | Implement backend service logic for campaign creation, including scheduling tools, budget limits, and audience targeting controls. | Y | 2025-04-27 | 2025-04-28 | 100% | Kuldeep
11 | 04. Advertisement Management. | 4.02 | Manage Sponsored Listings | Build and deploy analytics dashboard to monitor clicks, impressions, and returns on investment (ROI) for each sponsored listing. | Y | 2025-04-28 | 2025-04-29 | 100% | Dezil
12 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Design backend for sponsored listing priority system | Y | 2025-04-29 | 2025-04-30 | 100% | Fouzan
13 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Create UI for managing sponsored listings | N | 2025-04-30 | 2025-05-01 | 100% | Saily
14 | 04. Advertisement Management | 4.02 | Manage Sponsored Listings | Implement budget tracking for sponsored listings | Y | 2025-05-01 | 2025-05-02 | 100% | Kuldeep
15 | 05. Finance and Operations | 5.03 | Process Payments | Develop scheduled payout system for vendor bank accounts using integration with Stripe/PayPal APIs, with dashboard for audit logs. | Y | 2025-04-30 | 2025-05-01 | 100% | Fouzan
16 | 07. Customer Support | 7.03 | Submit Feedback | Enable customers to submit text feedback with a built-in sentiment analysis engine that classifies positive, neutral, and negative responses. | N | 2025-04-29 | 2025-04-30 | 100% | Tarun
17 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Implement a feedback analytics module that converts user ratings into experience scores using sentiment detection algorithms. | Y | 2025-04-30 | 2025-05-01 | 100% | Kuldeep
18 | 07. Customer Support | 7.06 | Manage Support Tickets | Develop a support ticketing system with escalation rules, SLA tracking, resolution stages, and assignment to appropriate support teams. | Y | 2025-05-02 | 2025-05-03 | 100% | Fouzan
19 | 07. Customer Support | 7.06 | Manage Support Tickets | Allow Diners to Submit Support Tickets | Y | 2025-04-18 | 2025-04-21 | 100% | Saily
20 | 07. Customer Support | 7.06 | Manage Support Tickets | API Endpoint to Create Support Tickets | Y | 2025-04-22 | 2025-04-26 | 100% | Fouzan
21 | 07. Customer Support | 7.06 | Manage Support Tickets | View Support Tickets in Restaurant Dashboard | Y | 2025-04-30 | 2025-05-03 | 100% | Tarun
22 | 07. Customer Support | 7.06 | Manage Support Tickets | API to Fetch Tickets for Restaurant | Y | 2025-04-19 | 2025-04-20 | 100% | Saily
23 | 07. Customer Support | 7.06 | Manage Support Tickets | Add Support Ticket Table in Database | Y | 2025-05-01 | 2025-05-06 | 100% | Kuldeep
24 | 04. Advertisement Management. | 4.01 | Create Ad Campaigns | Fetch and Display Campaigns in React | Y | 2025-04-17 | 2025-04-19 | 100% | Saily
25 | 04. Advertisement Management. | 4.01 | Create Ad Campaigns | implement Backend API for Campaign Retrieval | Y | 2025-04-18 | 2025-04-21 | 100% | Saily
26 | 04. Advertisement Management. | 4.01 | Create Ad Campaigns | Secure Campaign Access via JWT Middleware | Y | 2025-04-19 | 2025-04-22 | 100% | Kuldeep
27 | 04. Advertisement Management. | 4.01 | Create Ad Campaigns | Format Budget and Metrics in Campaign Table | Y | 2025-04-20 | 2025-04-23 | 100% | Fouzan
28 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Implement API endpoint to create a new reservation | Y | 2025-04-21 | 2025-04-23 | 100% | Kuldeep
29 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Implement API for restaurant owner to view all reservations | Y | 2025-04-22 | 2025-04-24 | 100% | Fouzan
30 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Add reservation modal to restaurant detail page | Y | 2025-04-23 | 2025-04-27 | 100% | Saily
31 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Show diner reservations in profile | Y | 2025-04-24 | 2025-04-26 | 100% | Kuldeep
32 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Prevent reservation submission if inputs are invalid | Y | 2025-04-25 | 2025-04-27 | 100% | Fouzan
33 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Display feedback on successful reservation submission | Y | 2025-04-26 | 2025-04-28 | 100% | Saily
34 | 02. Restaurant Management | 2.06 | Manage Table Reservations | Add cancellation capability for user reservations | Y | 2025-04-27 | 2025-04-30 | 100% | Fouzan
35 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Develop POST /ratings endpoint with business logic and validations | Y | 2025-04-28 | 2025-05-01 | 100% | Saily
36 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Create reusable React component for star-based rating input | Y | 2025-04-29 | 2025-05-02 | 100% | Fouzan
37 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Connect RatingForm to backend API and manage UI states | Y | 2025-04-30 | 2025-05-03 | 100% | Tarun
38 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Show rating form only for diners on restaurant detail page | Y | 2025-05-01 | 2025-05-04 | 100% | Saily
39 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Prevent users from rating the same restaurant multiple times | Y | 2025-05-02 | 2025-05-05 | 100% | Tarun
40 | 07. Customer Support | 7.04 | Rate Restaurant Experience | Add backend validation for rating submission | Y | 2025-05-03 | 2025-05-06 | 100% | Dezil